INITIATIVE CHARTER · PROJECT NORTH STAR

Store Technology Refresh

Replace end-of-life POS and equip 500 stores with associate-mobility devices by Q4 2026.

| SPONSOR | SVP, Store Operations |
| --- | --- |
| OWNER | Director, Store Technology |
| PROGRAM | Project North Star, Enterprise Transformation |
| VERSION | v3.2 · Approved · 22 September 2026 |
| DURATION | M8 to M36 (28 months, from vendor selection through full deployment) |

OBJECTIVE

Replace end-of-life point-of-sale hardware in all 500 Maple Retail stores and equip store associates with mobile devices that support clienteling, mobile checkout, and real-time inventory lookup on the sales floor. Full deployment by end of Q4 2026, benefits realization gate at M36.

VALUE HYPOTHESIS

$62M NPV over 5 years driven by three effects:

- +180 basis points conversion uplift from clienteling and reduced checkout friction (validated at +140bps in 10-store pilot)

- –30% checkout time at peak (labor productivity + reduced queue abandonment)

- Reduced hardware TCO from consolidated device management + retirement of legacy maintenance contracts

IN SCOPE

- Point-of-sale hardware and software refresh across all 500 stores

- Associate mobility devices (~4,500 units) and mobile POS software

- Network capacity assessment and remediation as required

- Associate training and change management for POS + mobility

- Retirement of legacy POS platform and associated licensing

OUT OF SCOPE

- Back-office ERP modernization (separate workstream: Merchant Tools)

- Customer-facing loyalty rebuild (separate workstream: Digital Loyalty Reboot)

- Payment gateway migration (adjacent workstream, sequenced with Wave 1)

- Distribution centre automation (separate workstream: Supply Chain Velocity)

SUCCESS CRITERIA

- Wave 1 (150 stores) complete by end of Q1 2027 with rollout velocity ≥ 40 stores/week

- Post-rollout conversion uplift within ±40bps of pilot result on rolling 90-day basis

- Checkout time p95 reduced by ≥ 25% at scale

- Zero material P1 incidents attributable to the new platform in the first 90 days post-Wave 1

KEY MILESTONES

| MILESTONE | DESCRIPTION | TARGET DATE | STATUS |
| --- | --- | --- | --- |
| M8 | Vendor selection complete | Mar 2026 | Complete |
| M12 | 10-store pilot with production POS + associate mobility | Jul 2026 | Complete · +140bps conversion |
| M18 | Wave 1 rollout (150 stores) | Jan 2027 | On track pending D-14 |
| M28 | Wave 2 rollout (250 stores) | Nov 2027 | Not started |
| M36 | Full deployment + benefits realization gate | Jul 2028 | Not started |

TOP RISKS (SEE FULL LOG IN TRACKER WORKBOOK)

- R-11 · Rural connectivity: 80 stores below spec. $4.2M remediation requested at Q3 SteerCo (D-14).

- R-17 · Change fatigue: Field survey shows fatigue 18pp above program threshold. Velocity revised down 20% + $400k OCM budget expansion.

- R-25 · Payment gateway adjacency: Gateway migration re-timed to avoid Wave 1 overlap. Regression test plan in place.

GOVERNANCE

Reports to the Q3 2026 Project North Star Steering Committee. Weekly workstream review Fridays with SVP Store Ops. Monthly deep-dive with CTO on payment gateway adjacency. Escalation path: Director Store Technology → SVP Store Ops → EC.

CHANGE CONTROL

Material scope changes (>$500k or >4-week schedule impact) require SteerCo approval. All changes logged in the TMO Change Register and referenced against original charter version.

Distributed to: Executive Committee · Store Technology WS · TMO · FP&A · Internal Audit