## Slide 1
PROJECT
North Star
Q3 2026 Steering Committee
Program status, three decisions required, and the portfolio outlook.
PRESENTED TO
Executive Committee · 22 October 2026
Prepared by the Transformation Management Office
Notes: Title slide. Open by naming the three decisions we need today so the audience is oriented. Do not walk through slide 1 in detail.

## Slide 2
PROJECT NORTH STAR
Q3 2026 STEERING COMMITTEE · CONFIDENTIAL
Maple Retail · Transformation Management Office
Page 2 of 10
DECISIONS REQUIRED TODAY
Three decisions. Twenty minutes.
Each carries a specific consequence if deferred.
DECISION
OWNER ASKS EC TO
COST OF DEFERRING
REC.
D-14 Approve $4.2M scope expansion to include rural network upgrade in Wave 1
Approve funding + timing shift of 6 weeks
~80 stores stranded in Wave 2 without connectivity; +$1.1M rework
APPROVE
D-15 Confirm sunset date for legacy loyalty platform (Q2 2027 vs. Q4 2027)
Pick a date; CDP cannot design cutover without it
Two workstreams blocked. Slip already 8 weeks and growing.
Q2 2027
D-16 Accept revised value forecast: $172M NPV (from $180M)
Acknowledge; reset benefits realization targets
Continued misalignment between finance and TMO reporting
ACCEPT
Backing detail on slides 5–7. Slide 10 is the ask if time runs short.
Notes: This is the single most important slide. If we only get through one slide, this is it. Read the three IDs, the ask, and the cost of deferring. Do not walk the RAG chart before this slide.

## Slide 3
PROJECT NORTH STAR
Q3 2026 STEERING COMMITTEE · CONFIDENTIAL
Maple Retail · Transformation Management Office
Page 3 of 10
PORTFOLIO AT A GLANCE
Two green, two amber, one red.
The reds and ambers concentrate in the same dependency chain.
5
ACTIVE WORKSTREAMS
$47M
VALUE REALIZED YTD
67%
MILESTONES ON PLAN
8 wk
CRITICAL PATH SLIP
WORKSTREAM
SCHED.
SCOPE
BUDGET
BENEFITS
OVERALL
Store Technology Refresh
Green
Unified Customer Data Platform
Red
Supply Chain Velocity
Green
Digital Loyalty Reboot
Amber
Merchant Tools Modernization
Amber
Notes: Portfolio view. Point at the concentration: CDP and Loyalty are the same dependency chain. Store Tech and Supply Chain are healthy. Don't dwell, get to the decisions.

## Slide 4
PROJECT NORTH STAR
Q3 2026 STEERING COMMITTEE · CONFIDENTIAL
Maple Retail · Transformation Management Office
Page 4 of 10
WHAT CHANGED SINCE LAST STEERCO
Three material shifts. One is good news.
PROGRESS WORTH NOTING
Store Tech pilot exceeded target
+140bps conversion vs. +100bps hypothesis. Wave 1 unblocked.
Supply Chain WMS cutover completed on time
No material incidents. $8M run-rate benefit confirmed.
Loyalty rebuild scope reduced 12%
Descope workshop closed 3 low-value features; NPV impact minimal.
NEW RISKS AND SLIPS
CDP integration slipped 6 weeks
Vendor delivered API layer late. Cascade risk to loyalty and merchant WS.
Rural connectivity gap discovered
Field survey found 80 stores below spec. $4.2M to remediate (D-14).
Merchant tools change fatigue signal
Field survey shows fatigue 18pp above program threshold. Velocity down 20%.
Notes: Two columns. Greens on the left, reds on the right. Do NOT skip the greens; they earn credibility for the reds. Move quickly through this slide (~90 seconds).

## Slide 5
PROJECT NORTH STAR
Q3 2026 STEERING COMMITTEE · CONFIDENTIAL
Maple Retail · Transformation Management Office
Page 5 of 10
DECISION D-14 · RURAL CONNECTIVITY
Fund the network upgrade now, or reshape Wave 2.
Field survey identified 80 stores where current bandwidth cannot support new POS + mobility devices.
OPTION A · EXPAND SCOPE NOW · RECOMMENDED
+$4.2M capex, 6-week schedule shift
Preserves Wave 1 rollout sequence
Rural stores land alongside peers, no brand-equity issue
Vendor pricing locked at Q3 rate
OPTION B · DEFER TO WAVE 2
No incremental cost this year
80 stores held back, brand equity risk
Rework est. $1.1M when re-integrated
Vendor pricing exposure carried to 2027
TMO RECOMMENDATION
Approve Option A.
The $4.2M is genuine incremental spend, but $1.1M of it comes back as avoided rework. Net exposure sits at $3.1M against a program benefit envelope of $172M NPV, well inside decision authority thresholds.
IF EC APPROVES TODAY
Vendor SOW signed by 5 Nov
Wave 1 sequence updated in plan
Rural stores enter Wave 1B, land Feb 2027
Notes: D-14 detail. Frame the ask as risk-adjusted: net exposure is $3.1M, not $4.2M, because avoided rework recoups $1.1M. Anchor on the vendor pricing lock as the timing driver.

## Slide 6
PROJECT NORTH STAR
Q3 2026 STEERING COMMITTEE · CONFIDENTIAL
Maple Retail · Transformation Management Office
Page 6 of 10
DECISION D-15 · LOYALTY SUNSET DATE
Open for 8 weeks. Two workstreams are waiting.
The CDP workstream cannot design migration without a firm cutover date. Loyalty cannot finalize comms.
RECOMMENDED
Q2 2027
Aggressive but achievable. Aligns with Store Tech Wave 1 close.
SAFER
Q4 2027
Adds $6M in dual-run costs. Loyalty benefits slip 6 months.
NOT RECOMMENDED
Defer again
Compounds slip. Two workstreams stay blocked.
WHAT'S STALLING THE DECISION
Concern about member communications during holiday 2026
Ownership dispute: Marketing vs. Digital
Uncertainty on data-migration effort
TMO RESOLUTION PROPOSAL
Q2 2027 cutover, staged member comms starting January
Marketing owns comms plan; Digital owns platform migration
Data migration scoped at 14 weeks (validated with vendor)
Notes: D-15 detail. Emphasize this is the SECOND time we've asked. The cost of another deferral is CDP and Loyalty re-baselining: $3M dual-run, $4M NPV erosion, 12wk slip.

## Slide 7
PROJECT NORTH STAR
Q3 2026 STEERING COMMITTEE · CONFIDENTIAL
Maple Retail · Transformation Management Office
Page 7 of 10
VALUE REALIZATION
$47M realized. $8M at risk. Forecast reset to $172M.
Decision D-16 asks the EC to accept the revised forecast and reset benefits targets.
$47M
REALIZED YTD
$125M
REMAINING FORECAST
$8M
VALUE AT RISK
$172M
REVISED NPV TARGET
WORKSTREAM
ORIGINAL NPV
REVISED NPV
Δ
DRIVER OF CHANGE
Store Technology Refresh
$62M
$66M
+$4M
Pilot outperformed on conversion
Unified Customer Data Platform
$38M
$32M
–$6M
Delayed activation cuts year-1 benefit
Supply Chain Velocity
$44M
$46M
+$2M
WMS savings running ahead
Digital Loyalty Reboot
$22M
$18M
–$4M
Scope descope + late sunset
Merchant Tools Modernization
$14M
$10M
–$4M
Adoption velocity down 20%
Portfolio
$180M
$172M
–$8M
Net of gains and losses
Notes: Honest forecasting slide. The $8M erosion is the point. Do not gloss it. Store Tech and Supply Chain gains offset half the loss, which is why the pitch on D-14 (which unlocks more Store Tech benefit) matters.

## Slide 8
PROJECT NORTH STAR
Q3 2026 STEERING COMMITTEE · CONFIDENTIAL
Maple Retail · Transformation Management Office
Page 8 of 10
TOP PROGRAM RISKS
Five risks matter this quarter. Two need EC action.
ID
RISK
PROB.
IMPACT
MITIGATION
R-08
Legacy loyalty sunset undecided
High
High
D-14 today. If deferred, CDP and Loyalty WS require re-baseline.
R-11
Rural connectivity gap
High
Med
D-14 today. Vendor SOW ready to sign on approval.
R-14
CDP vendor performance
Med
High
Weekly delivery review; contract remedies in play; parallel alt-vendor scan.
R-17
Field change fatigue
Med
Med
Rollout velocity revised down 20%; OCM budget +$400k for extended field support.
R-19
Finance / TMO reporting misalignment
Low
Med
D-16 today. Joint recalibration session scheduled 5 Nov.
Notes: Risk view. Note: R-08 and R-11 both point at decisions on this deck (D-15 and D-14). Do not walk through all five. Call out the two that need EC action and the top-right red R-14 (CDP vendor).

## Slide 9
PROJECT NORTH STAR
Q3 2026 STEERING COMMITTEE · CONFIDENTIAL
Maple Retail · Transformation Management Office
Page 9 of 10
NEXT 90 DAYS
What the EC should expect to see and when.
MILESTONE
WORKSTREAM
TARGET
CONFIDENCE
Wave 1 rollout begins (150 stores)
Store Tech
Nov 2026
High
CDP API contract remedy resolved
CDP
Nov 2026
Med
Loyalty cutover plan signed off
Loyalty
Dec 2026
Med · pending D-15
Distribution centre 3 automation live
Supply Chain
Dec 2026
High
Merchant tools pilot expansion
Merchant
Jan 2027
Med
Q1 2027 SteerCo · benefits gate review
Portfolio
Jan 2027
Confirmed
WHAT THE EC WILL BE ASKED NEXT QUARTER: approve Wave 2 sequencing, review revised NPV forecast against actuals, decide on merchant tools scope for FY27.
Notes: Forward view. Confidence column is the point. Med with a reason is honest. Do not walk each row; the audience can read.

## Slide 10
THE ASK
Page 10 of 10
If we have five minutes,
this is what we need from you.
DECISION 1 · D-14
Approve $4.2M rural connectivity scope expansion.
DECISION 2 · D-15
Confirm Q2 2027 as legacy loyalty sunset date.
DECISION 3 · D-16
Accept revised $172M NPV portfolio target.
Next SteerCo: 23 January 2027. Weekly Exec Decisions memo continues Fridays.
Notes: Closing slide. Pause after reading each decision. If you sense hesitation on any, offer to defer to next SteerCo, but name what that costs (see slide 6 for D-15 cost).