## Dashboard
PROJECT NORTH STAR · TMO
Portfolio Dashboard
October 2026 · Refreshed weekly · Owner: TMO Lead
VALUE REALIZED YTD |  |  | MILESTONES ON PLAN |  |  | CRITICAL PATH SLIP |  | BUDGET UTILIZED
|  |  | 67% |  |  | 8 wk |  | 38%
+$3.2M vs. plan |  |  | –8pp vs. last SteerCo |  |  | Loyalty + CDP dependency |  | $76M of $200M capex
WORKSTREAM RAG STATUS
WORKSTREAM | SCHEDULE | SCOPE | BUDGET | BENEFITS | OVERALL | OWNER | % COMPLETE
Store Technology Refresh | G | G | A | G | Green | SVP Store Ops | 42%
Unified Customer Data Platform | R | A | G | A | Red | VP Data & Analytics | 28%
Supply Chain Velocity | G | G | G | G | Green | VP Supply Chain | 55%
Digital Loyalty Reboot | A | R | G | A | Amber | CMO | 22%
Merchant Tools Modernization | A | G | A | A | Amber | VP Merchandising | 31%
MILESTONE HIT-RATE · TRAILING 6 MONTHS
| May | Jun | Jul | Aug | Sep | Oct
Actual Hit Rate | 82% | 86% | 78% | 80% | 71% | 67%
Target | 85% | 85% | 85% | 85% | 85% | 85%
Δ vs. Target
VALUE REALIZED · PORTFOLIO ROLL-UP (LINKED FROM VALUE TAB)
Workstream | PLAN NPV ($M) | FORECAST NPV ($M) | ACTUAL YTD ($M) | VARIANCE
Store Technology Refresh
Unified Customer Data Platform
Supply Chain Velocity
Digital Loyalty Reboot
Merchant Tools Modernization
PORTFOLIO

## Risk Log
PROJECT NORTH STAR · TMO
Risk & Dependency Log
27 open items · refreshed weekly · owner: TMO
SUMMARY
Open |  | Escalated |  | Mitigating |  | Closed
ID | TYPE | RISK / DEPENDENCY | WORKSTREAM | PROB | IMPACT | SCORE | OWNER | STATUS | MITIGATION / ACTION | OPENED | TARGET CLOSE
R-08 | R | Legacy loyalty sunset undecided. CDP and Loyalty WS blocked awaiting decision. | Loyalty | 3 | 3 |  | CMO | Escalated | D-15 requested at Q3 SteerCo. If deferred, CDP re-baseline; +$3M dual-run cost. | 2026-08-15 | 2026-10-22
R-11 | R | Rural connectivity below spec. ~80 stores affected. | Store Tech | 3 | 2 |  | SVP Store Ops | Escalated | D-14 requested at Q3 SteerCo. Vendor SOW ready to sign on approval; +$4.2M scope. | 2026-09-02 | 2026-10-22
R-14 | R | CDP vendor missed API delivery by 6 weeks. Cascade risk to loyalty and merchant. | CDP | 2 | 3 |  | VP Data | Mitigating | Weekly delivery review, contract remedies invoked, alt-vendor scan initiated. | 2026-09-10 | 2026-11-15
R-17 | R | Field change fatigue. Wave 1 rollout velocity risk. | Store Tech | 2 | 2 |  | Dir OCM | Mitigating | Rollout velocity revised down 20%; OCM budget +$400k; extended field support. | 2026-09-18 | 2026-12-01
R-19 | R | Finance / TMO benefits reporting misalignment | Portfolio | 1 | 2 |  | TMO Lead | Open | D-16 requested at Q3 SteerCo. Joint recalibration session scheduled 5 Nov. | 2026-09-25 | 2026-11-05
D-04 | D | DC3 automation → mobile POS inventory feed dependency | Supply/Store Tech | 1 | 2 |  | VP Supply Chain | Mitigating | API contract signed; integration test window Nov 12-16. | 2026-08-01 | 2026-11-16
D-07 | D | CDP customer record migration → Loyalty cutover data feed | CDP/Loyalty | 3 | 3 |  | VP Data | Open | Blocked pending D-15. Migration scoped at 14 weeks post-decision. | 2026-08-20 | 2026-12-15
R-22 | R | Merchant tools SME availability, Q1 gap in staffing | Merchant | 2 | 2 |  | VP Merch | Open | Contingent staffing plan in draft; expected approval Nov 15. | 2026-10-01 | 2027-01-31
R-25 | R | Payment gateway migration adjacency to Store Tech Wave 1 | Store Tech | 1 | 3 |  | CTO | Mitigating | Gateway migration re-timed to avoid Wave 1 overlap; regression test plan in place. | 2026-09-05 | 2026-11-30
R-06 | R | WMS cutover contingency plan needed | Supply Chain | 1 | 1 |  | VP Supply Chain | Closed | WMS cutover completed 15 Sep with no incidents. Contingency plan retained as reference. | 2026-06-10 | 2026-09-15
R-30 | R | Merchant training bandwidth constrained in Q1 | Merchant | 2 | 2 |  | VP Merch | Open | Assess dedicated trainer pool; explore vendor-provided training. | 2026-10-05 | 2027-02-28
R-31 | R | Store associate turnover higher than modeled in benefits case | Store Tech | 2 | 2 |  | SVP Store Ops | Open | HR partnering on turnover analysis; refresh training-cost model by Nov 30. | 2026-10-10 | 2026-11-30
D-11 | D | CDP → Merchant tools customer segmentation feed | CDP/Merchant | 2 | 2 |  | VP Data | Mitigating | Interim static-segment feed acceptable until Q2 27; documented workaround. | 2026-09-15 | 2027-04-30
R-33 | R | Cybersecurity review pending for CDP vendor SOC 2 evidence | CDP | 1 | 3 |  | CISO | Mitigating | Vendor SOC 2 Type II delivery expected Nov 20; contingent controls in place. | 2026-09-20 | 2026-11-20
R-35 | R | Wave 1 installer capacity, regional contractor concentration | Store Tech | 2 | 2 |  | SVP Store Ops | Mitigating | Second installer partner signed 10 Oct; capacity now dual-sourced. | 2026-08-25 | 2026-10-10
R-36 | R | Loyalty member communication risk during holiday 2026 | Loyalty | 2 | 2 |  | CMO | Open | Marketing developing staged comms plan; contingent on D-15 outcome. | 2026-10-01 | 2026-12-15
D-14 | D | Store Tech Wave 1 → Payment gateway sequence | Store Tech | 1 | 2 |  | CTO | Mitigating | Sequence re-confirmed at Oct 3 architecture review; on track. | 2026-08-10 | 2026-11-30
R-37 | R | Merchant tools OCM survey signal. Fatigue 18pp above threshold. | Merchant | 2 | 2 |  | VP Merch | Open | Deep-dive analysis with HR partners; discussion item next SteerCo. | 2026-10-12 | 2026-12-31
R-38 | R | DC3 automation vendor invoicing dispute (~$1.2M) | Supply Chain | 1 | 1 |  | VP Supply Chain | Open | Legal engaged; vendor billing team reviewing PO detail. No schedule impact. | 2026-09-28 | 2026-11-15
R-39 | R | Store Tech pilot conversion uplift may not scale to Wave 1 mix | Store Tech | 2 | 2 |  | SVP Store Ops | Mitigating | Pilot cohort skewed to urban; validation cohort added to Wave 1 first 20 stores. | 2026-10-01 | 2027-01-31
R-40 | R | Wave 1 network install, city permit delays in 3 municipalities | Store Tech | 1 | 1 |  | SVP Store Ops | Mitigating | Regional real estate team engaged; 2 of 3 permits secured; final expected Nov 8. | 2026-10-08 | 2026-11-08
D-15 | D | Loyalty comms platform → CDP identity resolution | Loyalty/CDP | 3 | 2 |  | CMO | Open | Blocked pending D-15 outcome. Identity mapping scoped once cutover confirmed. | 2026-09-05 | 2026-12-31
R-42 | R | Merchant tools UAT scope creep. 40+ new field requests. | Merchant | 2 | 2 |  | VP Merch | Open | Change control board convened; triage completed for 60% of requests. | 2026-10-05 | 2026-11-30
R-44 | R | CDP vendor SLA credits pending. Q3 shortfall $180k. | CDP | 1 | 1 |  | VP Data | Mitigating | Credit approved by vendor 8 Oct; expected in Q4 invoice. | 2026-09-30 | 2026-10-31
R-46 | R | Third-party integrator ramp-down risk post-Wave 1 | Store Tech | 2 | 2 |  | SVP Store Ops | Open | Knowledge transfer plan in draft; internal team capacity assessment scheduled. | 2026-10-14 | 2027-02-28

## Value Tracking
PROJECT NORTH STAR · TMO + FINANCE
Value Tracking Model
5-year NPV envelope · refreshed monthly · owners: TMO Lead + FP&A Director
WORKSTREAM | PLAN NPV ($M) | FORECAST NPV ($M) | ACTUAL YTD ($M) | VARIANCE | % REALIZED | CONFIDENCE | DRIVER OF FORECAST CHANGE
Store Technology Refresh | 62 | 66 | 12.4 |  |  | High | Pilot outperformed on conversion (+140bps vs +100bps)
Unified Customer Data Platform | 38 | 32 | 4.1 |  |  | Med | Delayed activation cuts year-1 benefit realization
Supply Chain Velocity | 44 | 46 | 22 |  |  | High | WMS savings running ahead of plan; DC3 automation on track
Digital Loyalty Reboot | 22 | 18 | 5.5 |  |  | Med | Scope descope + late sunset date compresses year-1 window
Merchant Tools Modernization | 14 | 10 | 3 |  |  | Low | Adoption velocity revised down 20% based on OCM data
PORTFOLIO | [6 empty] | Net of gains and losses; see slide 7 of SteerCo deck
MONTHLY VALUE REALIZATION · CUMULATIVE $M
Metric | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20
Plan | 0.5 | 2 | 5 | 9 | 14 | 20 | 28 | 35 | 43 | 51 | 58 | 65 | 72
Forecast | 0.5 | 1.8 | 4.5 | 8.5 | 13 | 19 | 26.5 | 33.5 | 41 | 48.5 | 55.5 | 62 | 68.5
Actual YTD | 0.5 | 1.8 | 4.5 | 8.5 | 13 | 19 | 26.5 | 34 | 42.5
Δ Actual vs. Plan
LEGEND
Blue text | Hardcoded input · edit here
Black text | Formula · do not edit
Portfolio row (navy) | Sum of workstream rows · do not edit
Note on C7: Baseline NPV signed off by board at program inception (Aug 2025). Do not overwrite without EC approval.
Note on D7: Current best-estimate NPV. Update monthly with FP&A. Change requires driver-of-change note in column I.